## Gantt Chart
THESISMATE: THESIS AND CAPSTONE MANAGEMENT SYSTEM
PROJECT TIMELINE (GANTT CHART) - JUNE 2026 to DECEMBER 2026
Pangasinan State University - Lingayen Campus ¦ BSIT
ACTIVITIES | STATUS | JUNE 2026 |  |  |  | JULY 2026 |  |  |  | AUGUST 2026 |  |  |  | SEPTEMBER 2026 |  |  |  | OCTOBER 2026 |  |  |  | NOVEMBER 2026 |  |  |  | DECEMBER 2026
|  | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1
A. SYSTEM DEVELOPMENT
Requirements Gathering & System Analysis | Completed | bar: JUNE 2026 WEEK 1 to JUNE 2026 WEEK 2
System Design (ERD, Database Schema, UI/UX Wireframes) | Completed | bar: JUNE 2026 WEEK 2 to JUNE 2026 WEEK 3
Development Environment Setup (.NET 10 / React 19 / SQL Server) | Completed | bar: JUNE 2026 WEEK 3
Authentication, 2FA & Account Management Module | Completed | bar: JUNE 2026 WEEK 3 to JUNE 2026 WEEK 4
User Management & Classroom Management Module | Completed | bar: JUNE 2026 WEEK 4 to JULY 2026 WEEK 1
Capstone Group Management Module | Completed | bar: JULY 2026 WEEK 1 to JULY 2026 WEEK 2
Chapter Submission & Review Module | Completed | bar: JULY 2026 WEEK 2 to JULY 2026 WEEK 3
Document Submission, Versioning & Review Module | Completed | bar: JULY 2026 WEEK 3 to JULY 2026 WEEK 4
Manuscript Collaboration Editor (Yjs CRDT + SignalR) | Completed | bar: JULY 2026 WEEK 3 to AUGUST 2026 WEEK 1
Consultation Scheduling & Logging Module | Completed | bar: JULY 2026 WEEK 4 to AUGUST 2026 WEEK 1
Defense Scheduling, Rubric & Rating Module | Completed | bar: AUGUST 2026 WEEK 1 to AUGUST 2026 WEEK 2
System Feature Tracker (Requirements Tracker) Module | Completed | bar: AUGUST 2026 WEEK 1 to AUGUST 2026 WEEK 2
Monitoring Dashboard & PDF Report Generation | Completed | bar: AUGUST 2026 WEEK 2 to AUGUST 2026 WEEK 3
Notifications & Cross-Cutting UI (Search, Theme, UI Kit) | Completed | bar: AUGUST 2026 WEEK 2 to AUGUST 2026 WEEK 3
Authorization Hardening & Upload Security (IGroupAccessChecker) | Completed | bar: AUGUST 2026 WEEK 3 to AUGUST 2026 WEEK 4
Unit & Integration Testing of Modules | Planned | bar: SEPTEMBER 2026 WEEK 1 to SEPTEMBER 2026 WEEK 4
System Refinement Based on Usability Findings | Planned | bar: OCTOBER 2026 WEEK 4 to NOVEMBER 2026 WEEK 2
Security Hardening & Deployment Configuration | Planned | bar: NOVEMBER 2026 WEEK 1 to NOVEMBER 2026 WEEK 3
System Finalization | Planned | bar: NOVEMBER 2026 WEEK 2 to NOVEMBER 2026 WEEK 4
B. MANUSCRIPT (DOCUMENTATION)
Title Proposal & Approval | Completed | bar: JUNE 2026 WEEK 1
Chapter 1 - Introduction (Background, Objectives, Scope) | Completed | bar: JUNE 2026 WEEK 1 to JUNE 2026 WEEK 2
Chapter 2 - Review of Related Literature & Studies | Completed | bar: JUNE 2026 WEEK 2 to JUNE 2026 WEEK 4
Chapter 3 - Methodology (Design, Tools, Evaluation Plan) | Completed | bar: JUNE 2026 WEEK 4 to JULY 2026 WEEK 2
Chapters 1-3 Consultation & Revisions | Completed | bar: JULY 2026 WEEK 2 to JULY 2026 WEEK 4
Post-Proposal Defense Manuscript Revisions | Completed | bar: AUGUST 2026 WEEK 2 to AUGUST 2026 WEEK 3
Class Orientation & Timeline Discussion (Capstone 2) | Completed | bar: AUGUST 2026 WEEK 4
Chapter 4 Discussion / Orientation | Planned | bar: SEPTEMBER 2026 WEEK 1
Chapter 5 Discussion / Orientation | Planned | bar: SEPTEMBER 2026 WEEK 2
Chapters 1-3 Refinement & Formatting | Planned | bar: SEPTEMBER 2026 WEEK 1 to SEPTEMBER 2026 WEEK 3
Chapter 4 - Results & Discussion Writing | Planned | bar: SEPTEMBER 2026 WEEK 1 to NOVEMBER 2026 WEEK 2
Chapters 4 & 5 Consultation | Planned | bar: OCTOBER 2026 WEEK 2 to NOVEMBER 2026 WEEK 2
Chapter 5 - Conclusions & Recommendations Writing | Planned | bar: OCTOBER 2026 WEEK 3 to NOVEMBER 2026 WEEK 2
Abstract, Preliminaries, CV & Other Parts | Planned | bar: NOVEMBER 2026 WEEK 1 to NOVEMBER 2026 WEEK 2
Manuscript Revisions and Hardbound Submission | Planned | bar: DECEMBER 2026 WEEK 1
C. TESTING, EVALUATION & DEFENSE
TITLE / PROPOSAL DEFENSE | Completed | bar: AUGUST 2026 WEEK 1
Usability Test Instrument Preparation (ISO 25010 Questionnaire) | Planned | bar: SEPTEMBER 2026 WEEK 4 to OCTOBER 2026 WEEK 1
PRE-FINAL DEFENSE | Planned | bar: OCTOBER 2026 WEEK 1
USABILITY TESTING WITH RESPONDENTS | Planned | bar: OCTOBER 2026 WEEK 2 to OCTOBER 2026 WEEK 3
Usability Test Data Analysis & Interpretation | Planned | bar: OCTOBER 2026 WEEK 3 to OCTOBER 2026 WEEK 4
Preparation for Final Defense | Planned | bar: NOVEMBER 2026 WEEK 2 to NOVEMBER 2026 WEEK 3
FINAL DEFENSE | Planned | bar: NOVEMBER 2026 WEEK 4
LEGEND
| Analysis / Planning | JUNE 2026 WEEK 4: Deployment Preparation
| Design & Setup | JUNE 2026 WEEK 4: Manuscript Writing
| Module Development | JUNE 2026 WEEK 4: Manuscript Consultation
| Security & Authorization | JUNE 2026 WEEK 4: Usability Testing
| Developer Testing | JUNE 2026 WEEK 4: Defense Milestone
| Refinement / Finalization | JUNE 2026 WEEK 4: Hardbound Submission
Status is reported as of Week 4 of August 2026 (baseline commit f130fd2). Completed = delivered and verified in the source tree; Ongoing = in progress; Planned = scheduled.
Source: SYSTEM_SPECIFICATIONS_STATUS.md v2.0 (2026-08-22) - functional requirements ~89% complete, non-functional requirements ~64% complete.
Prepared by:
KENNETH REY TABLANG
Researcher
Noted by:
CARLA CARMELA P. RAMOS, DIT
Subject-in-charge